Musina Local Municipality

h

HH

2015/16 SERVICE DELIVERY

AND

BUDGET IMPLEMENTATION PLAN

ANNUAL PERFORMANCE PROGRESS REPORT

Vision: “To be the’ vibrant, viable and sustainable gateway city to the rest of Africa”

Mission: “The vehicle of affordable quality services and stability, through Socio economic development and collective leadership”

VALUES

I - RESPECT

EFFICIENCY

TRANSPARENCY

ACCOUNTABILITY

EXCELLENCE

- INTRODUCTION AND BACKGROUND

The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA) section 69 (3) (b).

Circular 13 of the National Treasury stipulates that, “the SDBIP gives effect to the Integrated Development Plan (IDP) and the budget of the municipality and will be possible if the IDP and the budget are fully aligned with each other, as required by the MFMA.”

The budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan.

The SDBIP serves as the commitment by the municipality to realise the municipal objectives, the SDBIP projects planned level and standard of performance and specific achievements to be accounted upon implementation.

This is expressed in order to ensure that desired outcomes over the long term are achieved and are implemented by the administration over the next 12 months.

The Municipal Finance Management Act (MFMA) no 56 of 2003, defines the Service Delivery Budget Implementation Plan as a detailed plan approved by the Mayor of the municipality for implementing the municipality’s delivery of municipal services and its annual budget vote including service delivery targets and performance indicators for each quarter

- PURPOSE

The document presents the 2015/2016 Service Delivery and Budget Implementation Plan of the municipality drafted in compliance with the requirements of the MFMA.

The performance targets set in this document lay basis for the performance contracts of all Head of Departmental Heads and inform work plans and reportable matters for the department.

It enables the Council and the Municipal Manager to monitor the performance of the Municipal Manager and Managers directly Accountable to the Municipal Manager; and the community to monitor the performance of the municipality

- LEGAL REQUIREMENTS CONSIDERED WITH THE DEVELOPMENT/DESIGN OF THE SDBIP

Section 53 1(c) (ii) of the MFMA states that the Mayor must ensure that the municipality’s SDBIP is approved within 28 days after approval of the budget.

Section 69(3) of the MFMA states that the Accounting Officer must no later than 14 Days after the approval of the Budget submit the draft SDBIP and Performance Agreements for the Municipal Manager and all Senior Managers to the Mayor.

Sec 53 3(b) also states that the SDBIP’s must be made public no later than 14 days after its approval by Council and that the Performance agreements of the Municipal Manager, Senior Managers and any other categories of officials as may be prescribed, should be made public no later than 14 days after the approval of the SDBIP.

- REPORTING ON SDBIP

This section covers reporting on the SDBIP as a way of linking the SDBIP with the oversight and monitoring operations of the Municipal administration.

Various reporting requirements are outlined in the MFMA. Both the Mayor and the Accounting Officer have clear roles to play in preparing and presenting these reports.

The SDBIP provides an excellent basis for generating the reports for which MFMA requires.

The reports then allow the Municipality to monitor the implementation of service delivery programs and initiatives across the municipality.

  - QUARTERLY REPORTING

Section 52 (d) of the MFMA compels the mayor to submit a report to the municipal council on the implementation of the budget and the financial state of affairs of the municipality within 30 days of the end of each quarter. The quarterly performance projections captured in the SDBIP form the basis for the mayor’s quarterly report.

  - MID-YEAR REPORTING

Section 72 (1) (a) of the MFMA outlines the requirements for mid-year reporting. The accounting officer is required by the 25th January of each year to assess the performance of the municipality during the first half of the year taking into account:

(i) the monthly statements referred to in section 71 of the first half of the year

(ii) the municipalities service delivery performance during the first half of the financial year, and the service delivery targets and performance indicators set in the service delivery and budget implementation plan;

(iii) the past year’s annual report, and progress on resolving problems identified in the annual report; and

(iv) the performance of every municipal entity under the sole or shared control of the municipality, taking into account reports in terms of section 88 from any such entities.

Based on the outcomes of the mid-year budget and performance assessment report, an adjustments budget may be tabled if actual revenue or expenditure amounts are materially different from the projections contained in the budget or the SDBIP.

The SDBIP is also a living document and may be modified based on the mid-year performance review. Thus the SDBIP remains a kind of contract that holds the Municipality accountable to the community.

  - ANNUAL REPORTING

Section 46 (1) of Municipal Systems Act stipulates that a municipality must prepare for each financial year a performance report reflecting

(a) the municipality’s, and any service provider’s, performance during that financial year, also in comparison with targets of and with performance in the previous financial year;

(b) the development and service delivery priorities and the performance targets set by the municipality for the following financial year; and

(c) measures that were or are to be taken to improve performance

Sec 46 (2) further states that an annual performance report must form part of the municipality’s annual report in terms of Chapter 12 of the MFMA.

DEPARTMENT: MUNICIPAL MANAGER’S OFFICE

| Municipal Transformation And Organizational Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To provide administrative support to political office bearers whilst promoting needs and interests of our diverse community |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To promote the needs and interests of special focus groupings To deepen democracy and promote accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority area(IDP) | Project Name |  | Key performance indicator |  | Baseline |  | 2015/16 Annual Target |  | Q 1 Actual Performance |  | Q2 Actual Performance |  | Q3 Actual Performance |  | Q 4 Actual Performance |  | Total Annual Performance |  | Variance |  | Reason for Variance |  | Measures to Improve performance | Means of verification |  |
| SPECIAL PROGRAMME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Special Programmes | Batho pele |  | Number of Batho pele held |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Notices, Attendance register, invitation, programme/agenda |  |
| Special Programmes | Imbizo |  | Number of Imbizo held |  | 4 |  | 4 |  | 1 |  | 2 |  | 3 |  | 4 |  | 4 |  | 0 |  | None |  | None | Attendance register, invitation, programme |  |
| Public Participation | Ward Committees |  | Number of total Ward Committee Meetings Held |  | 72 |  | 72 |  | 16 |  | 31 |  | 47 |  | 57 |  | 57 |  | -15 |  | Unavailability of ward councillors due to other work commitments |  | Ward Committee meetings scheduled will be incorporated into a corporate calendar | Notice of Meetings; Attendance register and minutes of the meetings. |  |
| Public Participation | Ward Committees |  | Number Ward General Meetings held |  | 24 |  | 24 |  | 6 |  | 12 |  | 18 |  | 24 |  | 24 |  | 0 |  | None |  | None | Minutes and Registers of Ward General Meetings. |  |
| Special Programmes | Mandela day |  | Number of Mandela days celebrated |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Photos, memos, invoices |  |
| Special Programmes | Human rights day |  | Number of Human rights days celebrated |  | 1 |  | 1 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | None |  | None | Memos, Attendance register, agenda/ programme invitation |  |
| Special Programmes | Freedom day |  | Number of Freedom days celebrated |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | None |  | None | Memos, attendance register |  |
| Special Programmes | Women’s day |  | Number of Women’s days celebrated |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Attendance registers, Agenda/ programme, memos. |  |
| Special Programmes | Back to school campaigns |  | Number of Back to school campaigns conducted |  | 13 |  | 13 |  | 0 |  | 0 |  | 13 |  | 0 |  | 13 |  | 0 |  | None |  | None | Memos, Attendance Register |  |
| Special Programmes | Mayoral bursaries |  | Number of Mayoral bursaries awarded |  | 12 |  | 12 |  | 0 |  | 0 |  | 12 |  | 0 |  | 12 |  | 0 |  | None |  | None | Memos, Attendance register |  |
| Special Programmes | Marathon |  | Number of marathons coordinated |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Application form, Memos, photos, newsletter clips, Gazette |  |
| Special Programmes | Winter games |  | Number of Winter games coordinated |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Memos, fixture, photos |  |
| Budget | Mayoral Budget Speech |  | Number of Budget Speech held |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | None |  | None | Memos, attendance register, Agenda/ programme and invitation |  |
| Special Programmes | Gender forum programmes |  | Number of Gender Activities Conducted |  | 3 |  | 3 |  | 0 |  | 1 |  | 1 |  | 1 |  | 3 |  | 0 |  | None |  | None | Attendance Register, memo |  |
| Special Programmes | Senior citizens’ day |  | Number of Senior citizens’ days celebrated |  | 3 |  | 3 |  | 0 |  | 1 |  | 1 |  | 1 |  | 3 |  | 0 |  | None |  | None | Attendance register |  |
| Special Programmes | Children’s day |  | Number of Children’s days celebrated |  | 3 |  | 3 |  | 1 |  | 0 |  | 1 |  | 1 |  | 3 |  | 0 |  | None |  | None | Attendance register |  |
| Special Programmes | Moral regeneration programmes |  | Number of Moral Regeneration Activities Conducted |  | 3 |  | 3 |  | 1 |  | 0 |  | 0 |  | 1 |  | 3 |  | 0 |  | None |  | None | Attendance register |  |
| Special Programmes | Disability day |  | Number of Disability days celebrated |  | 3 |  | 3 |  | 0 |  | 1 |  | 1 |  | 2 |  | 3 |  | 0 |  | None |  | None | Attendance register |  |
| Special Programmes | HIV/AIDS council programmes |  | Number of HIV / AIDS Activities Conducted |  | 3 |  | 3 |  | 0 |  | 2 |  | 1 |  | 0 |  | 3 |  | 0 |  | None |  | None | Invites, Registers and Procurement Records |  |
| Oversight | Municipal Public Accounts Committee (MPAC) activities |  | Number of MPAC (Municipal Public Accounts Committee) meetings coordinated |  | 5 |  | 5 |  | 1 |  | 3 |  | 5 |  | 1 |  | 10 |  | +5 |  | The council approved annual programme necessitated that the committee meets more than initially targeted |  | The scope and focus of the oversight function must be aligned to the schedule of the oversight committee | Attendance register and Minutes |  |
| Youth | Youth Programme |  | Number of youth program conducted |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | None |  | None | Memos, Attendance register |  |
| Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Creating enabling communication environment that facilitates participation of stakeholders and promotes access to information and marketing municipal services. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To provide communication support services, public liaison, marketing, advocacy and events management activities within the municipality - To deepen democracy and promote accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority area(IDP) |  | Project Name |  | Key performance indicator |  | Baseline |  | 2015/16 Annual Target |  | Q 1 Actual Performance |  | Q2 Actual Performance |  | Q3 Actual Performance | Q 4 Actual Performance | Total Annual Performance |  | Variance |  | Reason for Variance |  | Measures to Improve performance |  |  | Means of verification |
| COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communication management |  | Communication strategy |  | Number of communication strategy reviewed |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 | 1 | 1 |  | 1 |  | None |  | None |  |  | Reviewed communication strategy and attendance register |
| Communication management |  | Media and marketing |  | Number of radio and newspaper features |  | 96 |  | 96 |  | 52 |  | 35 |  | 28 | 66 | 181 |  | +85 |  | High demand |  | None |  |  | Radio script and newspaper cutting |
| Communication management |  | Stakeholder relation |  | Number of communicators forums |  | 4 |  | 4 |  | 1 |  | 1 |  | 1 | 1 | 4 |  | 0 |  | 0 |  | None |  |  | Attendance register |
| Communication management |  | Website Maintenance |  | Updated website |  | 48 |  | 48 |  | 14 |  | 12 |  | 12 | 16 | 54 |  | +6 |  | High demand |  | None |  |  | Website Screen Prints outs |
| Communication management |  | Diversify communication systems |  | Number of bulk SMS’s issued |  | 96 |  | 96 |  | 32 |  | 38 |  | 40 | 31 | 141 |  | +45 |  | High demand of occasion, Eskom load shedding |  | None |  |  | Bulk sms print-outs |
| Communication management |  | Production and branding |  | Number of diaries produced |  | 600 |  | 500 |  | 0 |  | 500 |  | 0 | 0 | 500 |  | 0 |  | None |  | None |  |  | Diary designs |
| Communication management |  | Production and branding |  | Number of calendars produced |  | 7000 |  | 5000 |  | 0 |  | 5000 |  | 0 | 0 | 5000 |  | 0 |  | None |  | None |  |  | Designs calendars |
| Communication management |  | Production of speeches |  | Number of speeches produced |  | 12 |  | 12 |  | 19 |  | 14 |  | 17 | 21 | 71 |  | +59 |  | Many occasions, Community protests |  | None |  |  | Hard copies of Speeches |
| Communication management |  | Facebook update |  | Number of Facebook update |  | 48 |  | 48 |  | 82 |  | 41 |  | 41 | 41 | +205 |  | +157 |  | High demand |  | None |  |  | Facebook posts print-outs |

| Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deepen democracy through a refined ward committee model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To protect the municipality from potential risk. - To ensure reduction of fraud and corruption within the municipality - To protect the municipal properties and employees against potential threats. - To deepen democracy and promote accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority area(IDP) |  | Project Name | Key performance indicator | Baseline | 2015/16 Annual Target | Q1 Actual Performance |  | Q2 Actual Performance | Q3 Actual Performance |  | Q 4 Actual Performance |  | Total Annual Performance |  |  | Variance |  |  | Reason for Variance | Measures to Improve performance | Means of verification |  |
|  |  |  | RISK MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Management |  | Risk management services | Number of risk register developed | 1 | 1 | 0 |  | 0 | 0 |  | 1 |  | 1 |  |  | 0 |  |  | None | None | 1 Risk register |  |
| Risk Management |  | Risk management services | Number of risk management reports | 4 | 4 | 1 |  | 1 | 1 |  | 1 |  | 4 |  |  | 0 |  |  | None | None | Risk management report Audit committee minutes Council resolution |  |
| Risk Management |  | Risk management services | Number of Risk Committee meeting coordinated | 4 | 4 | 1 |  | 1 | 0 |  | 1 |  | 3 |  |  | -1 |  |  | Unavailability of members | Enforcement of meeting schedule. Forward planning in terms of issuing notices, reminders and where meetings do not materialise expediting alternate dates. | Minutes and attendance registers |  |
| Risk Management |  | Risk management services | Number of reviewed Risk Management policy | 1 | 1 | 0 |  | 0 | 0 |  | 0 |  | 1 |  |  | 0 |  |  | None | None | Risk management policy |  |
| Risk Management |  | Risk management services | Number of reviewed Risk Management st | 1 | 1 | 0 |  | 0 | 0 |  | 1 |  | 1 |  |  | 0 |  |  | None | None | Risk management strategy |  |
| Risk Management |  | Risk management services | Number of antifraud and corruption policies reviewed | 1 | 1 | 0 |  | 0 | 0 |  | 1 |  | 1 |  |  | 0 |  |  | None | None | Number of antifraud and corruption policy |  |
| Risk Management |  | Risk management services | Number antifraud and corruption awareness campaigns held | 4 | 4 | 1 |  | 1 | 1 |  | 1 |  | 4 |  |  | 0 |  |  | None | None | Attendance register Minutes of RMC |  |
| Risk Management |  | Risk management services | Number of security policies reviewed | 1 | 1 | 0 |  | 0 | 0 |  | 1 |  | 1 |  |  | 0 |  |  | None | None | Reviewed security policy |  |
| Risk Management |  | security reports | Number of times the security reports to be developed | 4 | 4 | 1 |  | 1 | 1 |  | 1 |  | 4 |  |  | 0 |  |  | None | None | Security reports |  |
| Risk Management |  | security awareness campaigns | Number of security awareness campaigns held | 4 | 4 | 1 |  | 0 | 1 |  | 0 |  | 2 |  |  | -2 |  |  | Non adherence to time schedule | Explore holding stand-alone awareness campaigns or tapping in general ward meeting. | Attendance Register |  |
| Risk Management |  | times security committee meetings | Number of times security committee meetings held | 4 | 2 | 0 |  | 0 | 0 |  | 0 |  | 2 |  |  | -2 |  |  | Non adherence to time schedule | Enforcement of meeting schedule. Forward planning in terms of issuing notices, reminders and where meetings do not materialise expediting alternate dates. | Attendance Register, Minutes |  |
| Risk Management |  | monthly meetings | Number of times monthly meetings coordinated | 12 | 12 | 0 |  | 3 | 2 |  | 3 |  | 8 |  |  | -3 |  |  | Non adherence to time schedule | Enforcement of meeting schedule. Forward planning in terms of issuing notices, reminders and where meetings do not materialise expediting alternate dates. | Attendance Register, Minutes |  |
| Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deepen democracy through a refined ward committee model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To provide independent objective assurance and consulting activities of the internal control systems, risk management and governance processes. - To ensure that issues raised by Auditor General are adequately addressed. - To strengthen accountability through proactive oversight. - To ensure effective and functional Internal Audit at the local municipalities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Name | Key performance indicator |  | Baseline | 2014/15 annual target | Q1 Actual Performance |  | Q2 Actual Performance | Q3 Actual Performance | Q4 Actual Performance |  | Total Annual Performance |  |  | Variance |  |  | Reason for Variance |  |  | Measures to Improve performance |  | Means of verification |
| INTERNAL AUDIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Effective Internal audit | Number of Internal audit plans approved |  | 1 | 1 | 0 |  | 0 | 0 | 1 |  | 1 |  |  | 0 |  |  | None |  |  | None |  | Audit Committee Approved Internal audit plan |
| Effective Internal audit | Number of internal audit projects completed |  | 9 | 9 | 2 |  | 2 | 2 | 3 |  | 9 |  |  | 0 |  |  | None |  |  | None |  | Internal Audit report Audit committee minutes |
| Effective Internal audit | Number of internal audit reports produced |  | 4 | 4 | 1 |  | 1 | 1 | 1 |  | 4 |  |  | 0 |  |  | None |  |  | None |  | Audit committee approved Reports |
| Effective Internal audit | Number of Audit Committee meetings coordinated |  | 4 | 4 | 1 |  | 1 | 1 | 1 |  | 4 |  |  | 0 |  |  | None |  |  | None |  | Attendance register, minutes |
| Effective Internal audit | Number of audit methodology reviewed |  | 1 | 1 | 0 |  | 0 | 0 | 1 |  | 1 |  |  | 0 |  |  | None |  |  | None |  | Reviewed audit methodology. Audit committee minutes |
| Internal audit | Effective Internal audit |  | Number of Audit committee charters reviewed | 1 | 1 |  | 0 | 0 | 0 | 1 |  | 1 |  |  | 0 |  |  | None |  | None |  | Council resolution Approved Audit committee charter |
| Internal audit | Internal Audit charters reviewed |  | Number of Internal Audit charters reviewed | 1 | 1 |  | 0 | 0 | 0 | 1 |  | 1 |  |  | 0 |  |  | None |  | None |  | Audit committee approved internal audit charter |
| Internal audit | Coordination of external audit (AGSA) processes. |  | percent of request and queries responded timeously | 100 | 100 |  | 0 | 0 | 100% | 0 |  | 100% |  |  | 0 |  |  | None |  | None |  | Auditor General Request register |
| Internal audit | audit action plans |  | Number of audit action plans developed and approved | 1 | 1 |  | 0 | 1 | 0 | 0 |  | 1 |  |  | 0 |  |  | None |  | None |  | Action plan 13/14 financial year audit Audit committee approval of the action plan |
| Internal audit | Resolution of audit findings |  | Number of 14/15 financial year audit findings resolved as per the action plan how many resolved?? | 27 | 19 |  | 0 | 0 | 0 | 19 |  | 19 |  |  | 0 |  |  | None |  | None |  | Tracking documents for request of information and management responses to audit findings |

DEPARTMENT: COMMUNITY SERVICES

| Municipal Transformation and Organizational Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Actions supportive of the human settlement outcome Implement a differentiated approach to municipal financing, planning, and support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To promote and enforce acceptable environmental practices To improve the quality of lives through social development and the provision of effective community services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority Area(IDP) | Project Name | Key Performance Indicator | Baseline | 2015/16 Annual Target | Q1 Actual Performance | Q2 Actual Performance | Q3 Actual Performance | Q4 Actual Performance | Total Annual Performance | Variance |  | Reason for Variance | Measures to Improve performance | Means of verification |
| LICENSING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| licensing | Compilation of driving schools data base | Number of driving schools data base Compiled | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | None | None | Database report |
| Purchase | Vehicle Testing Detector | Number of Vehicle testing detector purchased | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 |  | None | None | Vehicle Testing Detector machine Delivery note |
| Poles | Testing obstacle | Testing obstacle purchased | 21 | 21 | 0 | 0 | 21 | 0 | 21 | 0 |  | None | None | Testing obstacle machine Delivery note |
| licensing | Purchasing of the e-natis terminals | Number of e-natis terminals purchased | 5 | 3 | 0 | 0 | 0 | 0 | 0 | -3 |  | Budget constrains | Additional E-natis Terminals to be included as part of the new Traffic & Licensing Building | Report of the functional terminals |
| licensing | Testing learners licenses | Number of learners licenses | 96 | 96 | 41 | 29 | 82 | 27 | 179 | +83 |  | High demand | Adjust the target to reflect the changing need for the services. Increase the number of days in a week when this services is provided. | Statistics report RD 329 |
| licensing | Roadworthy test | Number of motor vehicles tested | 1200 | 1200 | 453 | 353 | 942 | 424 | 2172 | +972 |  | High demand | Adjust the target to reflect the changing need for the services. Increase the number of days in a week when this services is provided. | RD 329 |
| Law enforcement | Speed check | Number of Speed Checks conducted | 96 | 96 | 24 | 24 | 24 | 24 | 96 | 0 | None |  | None | Speed check Reports Schedule of speed checks |
| Traffic | Scholar patrol | Number of Patrols conducted | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 0 | None |  | None | Scholar patrol Reports Schedule of scholar patrols |
| Traffic | Road block | Number of Road Blocks conducted | 48 | 48 | 12 | 12 | 12 | 12 | 48 | 0 | None |  | None | Roadblock Reports Approval note Deployment plan Operational plan |
| Road Marking | Maintenance and easy access of the road infrastructure | Kilometres of all traffic routes | 20KM | 20KM | 5km | 5km | 5km | 5km | 20km | 0 | None |  | None | Quarterly operations and maintenance reports |
| Road signage | Installation of road signage | Number of signboards installed | 40 | 40 | 0 | 10 | 10 | 10 | 30 | -10 | Budget constrains |  | Establish a dedicated team that focuses on road signage and markings maintenance. | Quarterly signboards reports |
| Traffic | firearms and pouches purchase | Number of firearms and pouches purchased | 22 | 7 | 0 | 0 | 0 | 0 | 0 | -7 | Budget constrains |  | Optimise usage of current firearms and pouches | Purchasing order |
| Traffic | Arrive alive campaigns | Number of arrive alive campaigns conducted | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 0 | None |  | None | Arrive alive campaign Report |
| Traffic | Crime Prevention Workshops | Number of Crime Prevention Workshops held | 2 | 2 | 0 | 1 | 0 | 0 | 1 | -1 | Non adherence to time schedule |  | Collaborate and partner with organisations that operate within the crime prevention field. | Workshop Report |
| Social Services | new enrolments on the housing waiting list | Number of new enrolments on the housing waiting list | 0 | 80 | 200 | 200 | 300 | 0 | 700 | +620 | More application received |  | None | List of beneficiaries |
| Disaster | Food parcels/ grocery, clothing and blankets | Food parcels/ grocery, clothing and blankets | 4 | 4 | 2 | 1 | 2 | 0 | +5 | +1 | More disaster implications |  | Adjust the target to reflect the changing need for the services. | Inventory list |
| Social | satellites office visits | Number of satellites office visits | 2 | 8 | 3 | 2 | 2 | 0 | 7 | -1 | Non adherence to time schedule |  | Develop and adhere to a schedule of visits. | Schedule of sallites visits |
| Social services | MOU Review | Number of MOU reviewed | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | None |  | None | MOU Council Resolution |
| Disaster | Disaster Plan | Number of council approved disaster management plan | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | None |  | None | Existing DMP |

| WASTE MANAGEMENT, PARKS & RECREATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Waste Management |  | Number of parks maintained in Nancefield | 2 | 2 | 2 | 0 | 0 | 0 | 0 | -2 | The parks where cleaned periodically however due to structural defects, damage to fence and park equipment the target is not reached | Amend the technical description to indicate isolate maintenance on parks that is for the responsibility of the division and those that area responsibility of civil services | Site visits reports, pictures and completion certificates |
| Waste Management | Illegal dumping | Number of clean up campaigns conducted | 6 | 6 | 6 | 0 | 0 | 3 | 9 | 0 | More areas requiring cleaning | None | Attendance register for volunteer |
| Waste Management | Illegal dumping | Number of awareness campaigns conducted | 12 | 16 | 15 | 3 | 3 | 18 | 39 | +23 | More educational need on the awareness for the community | Collaborate and partner with organisations that operate within the environmental management field. Intensify messaging on various platforms. | Attendance register for participants |
| Waste Management | Refuse removal | Purchase of public bins | 0 | 60 | 0 | 0 | 0 | 0 | 0 | -60 | Budget constrains | Optimise usage of current bins | Delivery Note Asset Register |
| Waste Management | Refuse removal | 1 Compactor Truck purchased | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | None | None | Delivery note, invoice |
| Waste Management | Beautifying | Number of Island greened and beautifying on the N1 | 0 | 1 | 0 | 3 | 0 | 0 | 3 | +2 | The project was initial planned to be outsourced and a decision made to insource which resulted in greening and beautification of the Entrance to R508, N1 North and N1 South | Develop a greening programme and partner with social partners to ensure implementation thereof. | Site pictures, invoice and completion certificate |

DEPARTMENT: CORPORATE SERVICES

| Key Performance Area (KPA) 3: | Municipal Transformation and Organizational Development |
| --- | --- |
| Outcome 9: | Responsive, Accountable, Effective and Efficient Local Government System |
| Outputs : | Implement a differentiated approach to municipal financing, planning, and support |
| Strategic objectives | To increase institutional capacity, efficiency and effectiveness 1. Render administration functions 2. Records and information management 3. Manage facilities 4. Render secretariat services to committees 5. Manage Fleet Services (delegated to Technical Department) |

| Priority area(IDP) | Project Name | Key performance indicator | Baseline | 2015/16 Annual Target | Q1 Actual Performance | Q2 Actual Performance | Q3 Actual Performance | Q4 Actual Performance | Total Annual Performance | Variance | Reason for Variance | Measures to Improve performance | Means of verification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LEGAL SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Legal Services | By-laws development | Number of By-laws gazetted | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | None | None | Reports and By-Laws Public Participation Report Notices Council Resolution |
| Legal Services | Gazetting of By-Laws | Number of By-Laws developed | 3 | 1 | 0 | 0 | 0 | 3 | 3 | +2 | Transnational municipal arrangements | Rationalise all former Mutale and Musina Bylaws | By-laws gazetted Notice / Advert |
| Legal Services | Compliance and vetting of Policies | Number Compliant and vetted Policies | 40 | 10 | 0 | 0 | 0 | 11 | 11 | +1 | Transnational municipal arrangements | Rationalise and vet all policies | Review Report Vetting Process Plan |
| Legal Services | legal cases initiated or defended | Number of legal cases initiated or defended | 12 | 4 | 2 | 0 | 1 | 1 | 4 | 0 | None | None |  |
| Legal Services | Contracts development | Number of contracts drafted | 19 | 16 | 6 | 1 | 4 | 1 | 12 | -4 | Transnational municipal arrangements | Adjust the target to reflect the changing need for the services. Align target setting to realistic anticipated services in the financial year. | Contract Register Signed Contracts |
| Legal Services | legal opinions provided | Number of legal opinions provided | 3 | 4 | 0 | 0 | 1 | 0 | 1 | -3 | Less cases provided | Adjust target to reflect the need |  |
| Legal Services | Land Valuation | Number of supplementary Valuation Roll developed | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | None | None | Supplementary Valuation |
| Legal Services | Council | Number of ordinary council meetings held | 6 | 6 | 1 | 1 | 2 | 1 | 6 | 0 | None | None | Agenda, minutes |
| Legal Services | Council | Number of Special council meetings held | 3 | 2 | 2 | 1 | 1 | 1 | 5 | +3 | New municipal demarcation | None | Agenda, minutes |
| Administration | Departmental management | Number of Departmental management meetings held per time frames | 3 | 8 | 2 | 2 | 2 | 2 | 8 | 0 | None | None | Agenda, minutes |
| Administration | Departmental management | Number of Departmental general meetings held | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 0 | None | None | Agenda, minutes |
| Administration | Records management policy | Number of Records management policy reviewed | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | None | None | Adopted Reviewed Records management policy Council resolution |
| Administration | filing plan | Number of filing plan reviewed | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | None | None | Draft record management policy, Council resolution, LLF Minutes, Notice and employee consultative meeting, attendance registers |
| Administration | Contract manager Rental- external equipment | number of functional rented copiers provided to departments | 3 | 3 | 3 | 0 | 7 | 6 | 16 | +13 | Adjust the target to reflect the identified need taking into account the municipal growth. | None | Invoices paid monthly |
| Municipal Transformation and Organizational Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implement a differentiated approach to municipal financing, planning, and support |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To increase institutional capacity, efficiency and effectiveness 1. Render personnel admin services 2. Provide Occupational Development and Skills Development 3. Provide labour relations services |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Priority area (IDP) | Project Name |  | Key performance indicator |  |  | Baseline |  | 2015/16 Annual Target | Q1 Actual Performance |  | Q2 Actual Performance |  | Q3 Actual Performance |  | Q4 Actual Performance |  | Total Annual Performance |  | Variance |  | Reason for Variance |  | Measures to Improve performance | Means of verification |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HUMAN RESOURCE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Human Capital Management | Retention and Succession Plans |  | Number of retention and succession policy implemented |  |  | 0 |  | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Retention and Succession Plan. Council Resolution |  |
| Human Capital Management | Labour Relations |  | Percentage of referred cases attended to within 90 days |  |  | 6 |  | 3 | 0 |  | 3 |  | 2 |  | 0 |  | 5 |  | +2 |  | More cases |  | Ensure labour stability by ensuring that cases and grievances are settled as soon as possible | Labour relations report register |  |
| Human Capital Management | LLF meetings |  | Number of LLF meetings held |  |  | 4 |  | 4 | 1 |  | 1 |  | 1 |  | 1 |  | 4 |  | 0 |  | None |  | None | Minutes |  |
| Human Capital Management | LLF meetings |  | Number of LLF meetings cordinated |  |  | 4 |  | 4 | 1 |  | 1 |  | 1 |  | 1 |  | 4 |  | 0 |  | None |  | None | Minutes |  |
| Human Capital Management | Employee Wellness (Assistance) Programme |  | Number of Employee Wellness Interventions implemented |  |  | 1 |  | 4 | 1 |  | 1 |  | 1 |  | 1 |  | 4 |  | 0 |  | None |  | None | Reports |  |
| Human Capital Management | Employee Wellness (Assistance) Programme |  | Number of Annual Employee Wellness Programme Developed and Adopted |  |  | 0 |  | 2 | 0 |  | 1 |  | 0 |  | 1 |  | 2 |  | 0 |  | None |  | None | Reports |  |
| Human Capital Management | Training of employees |  | Number of employees trained as per workplace skills plan (WSP) |  |  | 100 |  | 100 | 23 |  | 4 |  | 72 |  | 2 |  | 101 |  | +1 |  | Training through grand funding from LGSETA |  | Align targets to planned training for the year | Training Reports |  |
| Human Capital Management | Workplace Skills Plan |  | Number of WSP (Workplace Skills Plan) submitted to LGSETA |  |  | 1 |  | 1 | 0 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | None |  | None | Copy and approval and proof of submission |  |
| Human Capital Management | Training Reporting |  | Number of Monthly Training reports generated and submitted |  |  | 12 |  | 12 | 3 |  | 3 |  | 3 |  | 3 |  | 12 |  | 0 |  | None |  | None | Proof of tabled reports to LLF or Training Committee. Proof of training Report Submission to the applicable SETA |  |
| Human Capital Management | compliance register |  | Number of compliance register developed and implemented |  |  | 1 |  | 4 | 1 |  | 1 |  | 1 |  | 1 |  | 4 |  | 0 |  | None |  | None | Compliance register Reports |  |
| Human Capital Management | implementation of the compliance register |  | Percentage of implementation of the compliance register in line with the Occupational Health and Safety Act |  |  | 4 |  | 4 | 1 |  | 1 |  | 1 |  | 1 |  | 4 |  | 0 |  | None |  | None | Reports |  |
| Human Capital Management | Employment Equity planning and reporting |  | Number of employment equity report submitted to Department of Labour (DoL) |  |  | 1 |  | 1 | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Equity reports Confirmation of submission. |  |
| Human Capital Management | Development and adoption of Employment Equity Policy |  | Number of Employment Equity Policy implemented |  |  | 1 |  | 1 | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Employment Equity Policy Council Resolution. |  |
| Human Capital Management | Develop and Adopts a 5 years Employment Equity Plan |  | Number of Employment Equity Plan Developed and Adopted by Council |  |  | 1 |  | 1 | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None | Employment Equity Plan. Council Resolution. |  |
| Human Capital Management | Induction of staff |  | Number of new employees inducted |  |  | 20 |  | 20 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -20 |  | No new appointments due to the municipal demarcation |  | Moved to 2016/2017 fy | Induction report |  |
| Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsive, Accountable, Efe and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A clear operational strategy that promotes operational efficiency. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To manage and coordinate the implementation of performance management systems (PMS) - To ensure compliance with the Performance Management System policy framework and Municipal Systems Act (MSA) - To ensure effective and efficient service delivery - To fully institutionalize performance monitoring and evaluation - To deepen democracy and promote accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority area(IDP) |  | Project Name |  | Key performance indicator | Baseline |  | 2015/16 Annual Target |  | Q1 Actual Performance | Q2 Actual Performance |  | Q3 Actual Performance |  | Q4 Actual Performance |  | Total Annual Performance |  | Variance |  | Reason for Variance |  | Measures to Improve performance |  |  | Means of verification |
| INFORMATION TECHNOLOGY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrated IT Services |  | IT Hardware (Procurement hardware equipment ) |  | Number of Workstations and notebook leased | 120 |  | 120 |  | 120 | 120 |  | 120 |  | 120 |  | 120 |  | 0 |  | None |  | None |  |  | Invoices |
| Integrated IT Services |  |  |  | Number of windows and office licenses | 120 |  | 120 |  | 120 | 120 |  | 120 |  | 120 |  | 120 |  | 0 |  | None |  | None |  |  | Purchased software |
| Integrated IT Services |  | Software |  | Number of users with licensed ProMIS Licensing | 5 |  | 5 |  | 4 | 0 |  | 5 |  | 0 |  | 9 |  | +4 |  | High demand |  | Align targets to contract entered for the year |  |  | Proof of payment to Fujitsu |
| Integrated IT Services |  | Software |  | Number of users with licensed ProMIS² - Expenditure (SCOA compliance) | 12 |  | 12 |  | 0 | 0 |  | 0 |  | 0 |  | 12 |  | 0 |  | None |  | None |  |  | Proof of payment to Fujitsu |
| Integrated IT Services |  | Software |  | Number of Payday License | 1 |  | 1 |  | 1 | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | None |  | None |  |  | Proof of payment to Payday |
| Integrated IT Services |  | Software |  | Number of Licenses for Traffic Control Software (Software for Traffic Fines) | 5 |  | 5 |  | 5 | 5 |  | 5 |  | 6 |  | 21 |  | +16 |  | More fines issued |  | Align targets to contract entered for the year |  |  | Proof of payment to TCS |
| Integrated IT Services |  | Meetings |  | Number of Steering Committee Meetings held | 4 |  | 4 |  | 1 | 0 |  | 0 |  | 0 |  | 1 |  | -3 |  | Non availability of members |  | ICT Steering Committee meetings schedule will be incorporated into a corporate calendar |  |  | Minutes |
| STRATEGIC OPERATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organisational performance management |  | Performance Agreements |  | Number of performance agreement MSA section 54 & 56 with completed and signed. | 6 |  | 6 |  | 6 | 0 |  | 0 |  | 0 |  | 6 |  | 0 |  | 0 |  | None |  |  | Signed performance agreement and proof of submission |
| Organisational performance management |  | Performance assessment / Evaluation |  | Number of performance reports assessed | 1 |  | 1 |  | 0 | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | None |  |  | Assessment Report |
| Organisational performance management |  | Planning |  | Number of Strategic Planning Session | 2 |  | 2 |  | 0 | 0 |  | 2 |  | 0 |  | 2 |  | 0 |  | 0 |  | None |  |  | Strategic Planning Report Council resolution |
| Organisational performance management |  | Development of 2015/2016 Service Delivery and Budget Implementation Plan (SDBIP) |  | Number of Organizational Service Delivery and Budget Implementation Plan (SDBIP) developed. | 1 |  | 1 |  | 0 | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | None |  |  | Copy of Organizational Service Delivery and Budget Implementation Plan (SDBIP) |
| Organisational performance management |  | Mid-Year Review of 2014/2015 Service Delivery and Budget Implementation Plan (SDBIP) |  | Number of Organizational Service Delivery and Budget Implementation Plan (SDBIP) reviewed. | 1 |  | 1 |  | 0 | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | None |  |  | Council resolution |
| Organisational performance management |  | Production of organizational performance report and project monitoring report. |  | Number of project monitoring reports produced | 4 |  | 4 |  | 1 | 1 |  | 1 |  | 1 |  | 4 |  | 0 |  | 0 |  | None |  |  | Copy of Projects monitoring reports |
| Monitoring and Evaluation |  | Production of outcome 9 and Local Government Turnaround Strategy (LGTAS) |  | Number of Outcome 9 and Local Government Turnaround Strategy (LGTAS) reports coordinated and produced | 4 |  | 4 |  | 1 | 1 |  | 1 |  | 1 |  | 4 |  | 0 |  | 0 |  | None |  |  | Back to basics reports |
| Reporting |  | Annual Performance Report |  | Number of Annual Performance Reports Developed | 1 |  | 1 |  | 1 | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | None |  |  | Copy of Annual Performance Reports |
| Reporting |  | Annual Report |  | Number of Annual Report Developed and Tabled | 1 |  | 1 |  | 1 | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | None |  |  | Council resolution |
| Oversight |  | Oversight report on the Annual report |  | Number of Council approved oversight report | 1 |  | 1 |  | 0 | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | None |  |  | Council resolution |
| Reporting |  | Mid-Year Performance Report |  | Number of Mid-Year Performance Report Tabled and Assessed | 1 |  | 1 |  | 0 | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | None |  |  | Council resolution |
| Meetings |  | Departmental Management meetings |  | Number of Departmental Management meetings held | 12 |  | 12 |  | 0 | 3 |  | 3 |  | 3 |  | 12 |  | 0 |  | 0 |  | None |  |  | Agenda and minutes |
| Meetings |  | Departmental general meetings |  | Number of Departmental general meetings held | 12 |  | 12 |  | 0 |  |  | 3 |  | 3 |  | 9 |  | -3 |  | Non adherence to time schedule |  | Develop and monitor adherence to a corporate calendar. Issue notices and reminders. |  |  | Agenda and minutes |
| Meetings |  | extended management meeting |  | Number of extended management meeting held | 2 |  | 2 |  | 0 | 1 |  | 1 |  | 0 |  | 2 |  | 0 |  | 0 |  | None |  |  | Agenda and minutes |

DEPARTMENT: FINANCE

| Municipal Financial Viability and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Compliance with MFMA and MBRR - Maximize collection of own revenue to support sustainability and enhance service delivery - Formulate & implement financial management policies and procedures that ensures correct payments of creditors within prescribed periods - Ensure proper management, control, safekeeping and usage of assets. - Maintain accurate, reliable audit records. - Administrative and financial capability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To prepare a credible and realistic budget in line with MFMA timelines. - To prepare and submit credible financial information to stakeholders on a monthly basis. - To ensure financial viability and sustainability - Enhance compliance with legislation and improve financial viability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority Area(IDP) | Project Name | Key Performance Indicator | Baseline | 2015/16 Annual Target | Q1 Actual Performance | Q2 Actual Performance | Q3 Actual Performance | Q4 Actual Performance | Total Annual Performance | Variance | Reason for Variance |  | Measures to Improve performance |  |  |  | Means of Verification |
| BUDGET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget and Reporting | Submit budget for approval by Council | Number of 2016/17 council approved Budget before 31st May 2015 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | None |  | None |  |  |  | Council resolution Agenda Minutes Attendance Register Notice Draft Budget Final Budget |
| Budget and Reporting | Submit Budget and IDP Time schedule for approval | Number of 2016/17 Budget & IDP Time schedule submitted by Council before 31st August 2015 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | None |  | None |  |  |  | Council resolution Agenda Minutes Attendance Register |
| Budget Reporting | Submit quarterly financial reports to council | Number of quarterly reports submitted within 30 days after end of quarter | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 0 | None |  | None |  |  |  | Council resolution Finance Committee Minutes |
| REVENUE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revenue management | Enhance compliance with legislation and improve financial viability | Percentage collection rate against billing | 85% | 90% | 88% | 90% | 90% | 90% | 90% | 0 | None | None |  |  |  |  | System report |
| Revenue management | Enhance compliance with legislation and improve financial viability | Number of monthly billings | 12 | 12 | 3 | 3 | 3 | 3 | 12 | 0 | None | None |  |  |  |  | System report |
| Revenue Management | Write off all qualifying debts from our debtors book | Irrecoverable debts written off | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | None | None |  |  |  |  | Council resolution and system reports |
| EXPENDITURE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expenditure Management | Perform payroll runs and reconciliations | Number of payroll runs and reconciliation | 12 | 12 | 3 | 3 | 3 | 3 | 12 | 0 | None |  |  | None |  |  | Payslips |
| Expenditure Management | Perform monthly bank reconciliations | Number of bank reconciliations performed | 12 | 12 | 3 | 3 | 3 | 3 | 12 | 0 | None |  |  | None |  |  | Signed bank reconciliation |
| Expenditure Management | Submit VAT 201 return to SARS monthly | Number of VAT 201 returns submitted | 12 | 12 | 3 | 3 | 3 | 3 | 12 | 0 | None |  |  | None |  |  | Proof of submission to SARS |
| Supply chain management | Monthly Stock taking | Number of stock take conducted | 12 | 12 | 3 | 3 | 3 | 3 | 12 | 0 | None |  |  |  | None |  | Monthly reports |
| Asset management | Quarterly Asset verification | Number of Asset verification conducted | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 0 | None |  |  |  | None |  | Quarterly reports |
| Supply Chain Management | Update supplier database once a year | Number of Updated supplier database | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | None |  |  |  | None |  | Proof of advertisement and updated database |
| Supply Chain Management | Evaluate, Adjudicate and award all bids | Percentage of bids evaluated, adjudicated and awarded within 90 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0 | None |  |  |  | None |  | Minutes of bid meeting, appointment letters, tender register, Tender adverts |
| REPORTING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Financial management | Compilation of GRAP compliant financial statements | Number of GRAP compliant Financial Statements produced | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | None |  |  |  |  | None | Audit committee resolution AGSA report |
| Budget and reporting | Prepare monthly section 71 report | Number of sec 71 reports | 12 | 12 | 3 | 3 | 3 | 3 | 12 | 0 | None |  |  |  |  | None | Section 71 report Proof of submission |

DEPARTMENT: TECHNICAL SERVICES

| TECHNICAL SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Performance Area (KPA) 5: |  |  |  | Basic Services Delivery |  |  |  |  |  |  |  |  |  |  |
| Outcome 9: |  |  |  | Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |
| Outputs: |  |  |  | Improving access to basic services Provide electrical services within the licensed area Provide civil & mechanical engineering services Ensure an environment that is not harmful to health and wellbeing of the community. Address municipal infrastructure backlog Provide and maintain water and sanitation services. |  |  |  |  |  |  |  |  |  |  |
| Strategic objectives |  |  |  | To initiate and improve the quantity and quality of municipal infrastructure and services |  |  |  |  |  |  |  |  |  |  |
| Project No. | Priority area (IDP) | Project Name | Key performance indicator | Baseline | 2015/16 Annual Target | Q1 Actual Performance | Q2 Actual Performance | Q3 Actual Performance | Q4 Actual Performance | Total Annual Performance | Variance | Reason for Variance | Measures to Improve performance | Means of verification |

WATER AND SANITATIONS

|  | Green drop | Water quality sampling and monitoring | Number of Samples blue and green drop water quality standards | 136 | 108 | 24 | 29 | 35 | 39 | 127 | +19 | More compliance requirements | Adjust targets in line with statutory requirements | Sample register Lab results |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Basic service delivery |  | Sourcing of Operation & Maintenance supplies (water) | Number of planned and maintenance work conducted ( Water supply annually) | 12 | 12 | 95 | 97 | 99 | 96 | 387 | +375 | The target understated and high demand of maintained works | Develop a maintenance schedule that is realistic, invest in upgrading infrastructure | Signed off job cards/progress reports Inventory list of supplies |
| Basic service delivery |  | Sourcing of Operation & Maintenance supplies (Sanitation) | Number of planned and maintenance work conducted (Sanitation Annually) | 8 | 8 | 83 | 79 | 104 | 68 | 334 | +326 | The target understated and high demand of maintained works | Develop a maintenance schedule that is realistic, invest in upgrading infrastructure | Signed off job cards/progress reports Inventory list of supplies |

| Priority area (IDP) | Project Name | Key performance indicator | Baseline | 2015/16 Annual Target | Quarter 1 Actual Performance | Quarter 2 Actual Performance |  | Quarter 3 Actual Performance | Quarter 4 Actual Performance | Total Annual Performance | Variance | Reason for Variance | Measures to Improve performance |  | Means of verification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CIVIL & MACHENICAL ENGINEERING SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Basic Service Delivery | To coordinate maintenance and up keep of municipal roads | Number of kilometre of roads with preventative maintenance completed | 2km | 2km | 0 km | 0 km |  | 0 km | 0 km | 0 km | -2km | Budget Constrains | Develop and implement a maintenance plan and schedule |  | Schedule Job Card Inventory of supplies Pictures |
| Basic Service Delivery | Clearing and cleaning of hydraulic structure | Percentage of hydraulic structures cleaned | 100% | 100% attendance to defects or requirements | 100% attendance to defects or requirements | 100% attendance to defects or requirement |  | 100% attendance to defects or requirements | 100% attendance to defects or requirement | 100% attendance to defects or requirements | 0 attendance to defects or requirement | None | None |  | Daily and pictorial report |
| Basic Service Delivery | Fleet Machinery | Maintain not less than 80% operational of equipment’s fleet and machineries | 80% | 80% of fleet availability to service delivery | 15.56% of fleet availability to service delivery | 15.56%of fleet availability to service delivery |  | 15.56% of fleet availability to service delivery | 15.56% of fleet availability to service delivery | 15.56% of fleet availability to service delivery | -65% fleet availability to service delivery | The target was not achieved due to lack of in-house workshop, parts availability and the calculation of the actual performance is affected by the growth on the asset register. | Simplify a target so that is not dependent on variables and complicated methods of calculation. In determining the target and reportable due consideration must be given to fleets and equipment on the council asset register which impacts on the volume of the denominator. |  | Resource commitment job card uninterrupted service delivery |
| Basic Service Delivery | To construct storm-water drainage in Musina | Number of km of Storm water constructed | 2km | 2km | 0 km | 0 km |  | 0 km | 0 km | 0 km | -2km | Budget Constrains | Develop a storm water infrastructure development plan. Prioritise roads maintenance and development |  | Progress report/ completion certificate |
| Roads | Construction of Speed humps | Number of traffic calming structures and pedestrian crossing redesign and reconstruction | 20 | 4 | 2 | 0 |  | 0 | 0 | 0 | -2 | Budget Constrains | Develop a storm water infrastructure development plan. Prioritise roads maintenance and development |  | Progress Report. Locations Inventory register. |
| Roads | To Re-gravel roads in Musina | Number of Kilometres of gravel roads, re-gravelled and blading | 300km | 300km | 0km | 19.1km |  | 128km | 45km | 202.1km | 0km | Additional needs in areas affected by road detoriations. | Adjust the target going forward |  | Re-gravelling report Pictures. |
| Roads | Maintenance, upgrading and refurbishment of municipal buildings | Maintenance requirement to the office space or buildings | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% attendance to defects or requirement | 0 | None | None |  | Maintenance schedule Completion report. Invoice. |
| ELECTRICAL ENGINEERING SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority area (IDP) | Project Name | Key performance indicator | Baseline | 2015/16 Annual Target | Quarter 1 Actual Performance | Quarter 2 Actual Performance | Quarter 3 Actual Performance |  | Quarter 4 Actual Performance | Total Annual Performance | Variance | Reason for Variance | Measures to Improve performance | Means of verification |  |
| Basic Service Delivery | operation and maintenance | Number of routine operation and maintenance of electrical infrastructure conducted | 5 | 20 | 53 | 75 | 83 |  | 55 | 266 | +246 | High demand in maintenance due to ageing infrastructure and theft and the target was under stated | Develop a maintenance plan that is reflective of operational trends | Electricity maintenance plan |  |
| Basic Service Delivery | Replacement of copper to aluminium conductor in Nancefield EXT 7 | Distance of Replacement of copper to aluminium Conductor done (Nancefield Ext 7 replacement of copper to aluminium conductor) | 0 | 8.5km | 0 | 0 | 0 |  | 8.23km | 8.23km | -0.27 | The target was overstated by 0.27 | Set realistic Targets | Completion certificate |  |
| Basic Service Delivery | Replacement and maintenance | Number of BEC 11 metres replaced to BEC 44 Meters | 0 | 80 households | 24 households | 25 households | 30 households |  | 25 households | 104 households | +24 households | Additional needs due to breakdowns and meter tempering inspections | Develop an infrastructure development plan | Completion certificate |  |
| Basic Service Delivery | Replacement and maintenance | Number of BEC 11 metres replace to BEC 23 Meters | 0 | 75 households | 0 households | 15 households | 20 households |  | 18 households | 53 households | -27 households | Budget Constrains | Develop an infrastructure development plan | Copy of works order and job card issued |  |

PMU

| Priority area (IDP) | Project Name | Key performance indicator | Baseline | 2014/15 annual target | Q1 Actual Performance | Q2 Actual Performance | Q3 Actual Performance | Q4 Actual Performance | Total Annual Performance | Variance | Reason for Variance | Measures to Improve performance | Means of verification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Traffic building | Traffic building | Number of traffic building constructed | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | None | None | Developed project specifications, appointement of service provider |
| Roads | Nancefield construction of roads | KM road to be constructed by concrete pave | 0 | 2.86km | 0 | 0 | 0 | 2.86km | 2.86km | 0 | None | None | Progress report Occupancy certificate Close up report Site Visit Report |
| Community Lighting | Nancefield high mast community lighting | Number of high masts to be installed | 25 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | None | None | Progress report Close up report Site Visit Report |
| Sport Centre | Madimbo Sport centre | Number of Sports Centres to be construction | 6 | 1 | 0 | 0 | 0 | 0 | -1 | -1 | Budget Constrains | Prioritise implementation of infrastructure projects on the budget | Progress report Occupancy certificate Close up report Site Visit Report |

DEPARTMENT: LOCAL ECONOMIC DEVELOPMENT

| Municipal Financial Viability and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Compliance with MFMA and MBRR - Maximize collection of own revenue to support sustainability and enhance service delivery - Formulate & implement financial management policies and procedures that ensures correct payments of creditors within prescribed periods - Ensure proper management, control, safekeeping and usage of assets. - Maintain accurate, reliable audit records. - Administrative and financial capability |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To prepare a credible and realistic budget in line with MFMA timelines. - To prepare and submit credible financial information to stakeholders on a monthly basis. - To ensure financial viability and sustainability - Enhance compliance with legislation and improve financial viability |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority Area(IDP) | Project Name | Key Performance Indicator | Baseline | 2015/16 Annual Target | Q1 Actual Performance | Q2 Actual Performance | Q3 Actual Performance | Q4 Actual Performance | Total Annual Performance | Variance | Reason for Variance | Measures to Improve performance | Means of Verification |
| IDP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategy and Planning | IDP, Budget | Number of IDP, Budget process plan approved | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | None | None | Agenda, Minutes and Council resolution |
| Strategy and Planning | IDP Furums | Number of IDP forums conducted | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 0 | None | None | Agenda, Minutes |
| Strategy and Planning | Meetings | Number of IDP Steering committee conducted | 7 | 7 | 3 | 2 | 1 | 1 | 7 | 0 | None | None | Agenda, Minutes |
| Strategy and Planning | IDP. Budget | 2 of council approved 2016/ 2017 IDP/ Budget | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 0 | None | None | Extract of the Council resolutions Copies of public notice, Agenda and minutes of the meetings together with attendance registers |
| Strategy and Planning | IDP Rating | COGHSTA Credibility Rating of 15/16 IDP | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | None | None | MEC Coghsta results reports |
| Strategy and Planning | Public participation | Number of IDP public participation | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | None | None | Public participation programme, reports and attendance registers from all 6 respective wards |
| TOWN PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Town Planning | Street naming policy | Number of street naming policy developed | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | None | None | advertisement, appointment letter, service contract, stakeholder engagement and public participation minutes, council resolution |
| LED |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Promotion of SMME products (exhibitions) | Number of exhibitions coordinated | 4 | 4 | 1 | 0 | 2 | 2 | +5 | +1 | High demand | None | Copies of invitation, programme and attendance register |
| Economic Development | Workshops | Number of workshops coordinated and conducted | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 0 | None | None | Copies of invitation. Attendance register and programme |
| EPWP | Job Creation and Monitoring | Number of jobs created through EPWP | 120 | 120 | 0 | 0 | +1251 | 0 | +1251 | +1131 | Creating more jobs for youth | Develop a maintenance plan that is reflective of operational trends | Filing of notices, recruitment records and appointments |
| LED Projects (Strategy and Planning) | Development of 2030 LED Strategy | Number of 2030 LED Strategy developed | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | None | None | Copies of invitation, attendance register and programme |